## Annex. No 4. Plan
EETS Domain Statement of the Republic of Lithuania
Annex No. 4.
STANDARD EETS PROVIDER ACCREDITATION PLAN
ID | Activity | Duration (calendar days) | Responsible | 1 month | 2 month | 3 month | 4 month | 5 month | 6 month
1 | Preparation for Accreditation
1.1 | Signing of the Accreditation Agreement | 5 | EETS Provider Candidate
1.2 | Payment of the Accreditation Fee | 14 | EETS Provider Candidate
1.3 | Alignment and approval of the Accreditation Plan | 5 | EETS Provider Candidate / Company
2. | Technical Infrastructure Setup
2.1 | Provision of Technical Infrastructure | 5 | Company
2.2 | Granting Access to the e-Tolling Infrastructure | 3 | EETS Provider Candidate
2.3 | Testing and Validation of Access and Infrastructure Readiness | 1 | EETS Provider Candidate / Company
3. | Testing Phase
3.1 | System Compatibility Testing | 60 | EETS Provider Candidate
3.2 | Device Testing | 60 | EETS Provider Candidate
3.3 | End-to-End System and Device Testing | 60 | EETS Provider Candidate
4. | Assessment of Test Results
4.1 | Submission of the Test Report | 14 | EETS Provider Candidate
4.2 | Evaluation of Test Results | 14 | Company
4.3 | Remediation of Identified Deficiencies | 30 | EETS Provider Candidate
4.4 | Accreditation Decision | 5 | Company
5 | Service Launch
5.1 | Signing of the Service Agreement | 10 | EETS Provider Candidate / Company
5.2 | Pilot Operation | 90 | EETS Provider
5.3 | Commencement of Service Provision |  | EETS Provider / Company